# Projects overview

Katrina

2025-02-04

### Mandarin question in laboratory phonology

- Establish the tone–intonation relationship using traditional laboratory phonology approaches, with particular emphasis on individual variability in intonation realisation.

- Serves as the foundation for further perception-related investigations.

#### Completed ✅

- 2024 Nov-Dec: record 8 people, initial analysis, prepare TAI abstract

- 2025 Jan-Mar: processing with LIBC interns

- 2025 May-June: TAI presentation; LIBC poster

- 2025 August: TAI proceeding

- 2025 Nov-Dec: collaboration meetings; record 7 people

- 2026 Jan: processing new recording with LIBC interns

Side-products

- Manual for segmentation (specifically for this task, but could potentially be expanded with other user cases)

- ShinyAPP to check f0 outliers, either by contour or point data: InterVisual

- ShinyAPP to visualise PCA results (from PCA scores to reconstructed contours): InterVisual-PCA

- A set of Praat scripts facilitating data processing and quality checks.

#### Current status ⏱️

- processing the 7 people data

#### Next steps ☑️

- 2026 Late Feb & Early March: Get in touch with Tong & Yao: new dataset; update results; article plan

- 2026 April-May: Write the article

### Non-canonical Q Handbook chapter

- A systematic review of the topic.

#### Completed ✅

- 2024 Aug-Oct: Syntax, semantics writing

- 2025 Jan-Apr: recording, prosody, first draft sent out

- 2025 Sep: new materials and recording, prosody

- 2025 Dec - 2026 Jan: second draft revising and sent out

#### Current status ⏱️

- Waiting for the second round review

#### Next steps ☑️

- Finalising, expected March(?)

### Non-canonical Q Experiment

- Focus: Investigate how prosody reflects subtle contextual differences across subtypes of question intonation, and how these interact with different morpho-syntactic forms.

#### Completed ✅

- 2025 July-August: Shumian visit, initiate the plan

- 2025 August-November: Experiment materials, online implementation and pilot

#### Current status ⏱️

- Original plan needs to be revised; an auditory rating task as the first step.

#### Next steps ☑️

- 2026 Feb: auditory rating experiment materials; set up the experiment on Gorilla

- 2026 Mar: rating experiment

- 2026 Apr-May: production data collection

- 2026 Jun-Aug: production data analysis, article write up in the last months or after

### Mandarin question in corpus (current status: on hold)

- Investigate tone–intonation interactions in spontaneous speech, as well as the question usages (morphosyntactic vs. prosodic) in real life.

#### Completed ✅

- 2024 Nov: trial processing of MagicData corpus

- 2025 Mar-Jun: detailed cleaning and checking of corpus

- 2025 Sep-Oct: turn-taking processing; prosodic patterns of three SFPs, for Dag van de Fonetiek